## Sheet1
Sr No | Action Item | Detailed Scope | Responsible | Target Date | Status | Department | Month | Audited By | Audit Date
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | closed | Beneficiation | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | completed | Beneficiation | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Completed | Beneficiation | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | In Progress | Pellet Plant | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Completed | Pellet Plant | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | In Progress | Pellet Plant | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Pellet Plant | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | In Progress | Beneficiation | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
8 | PLC Logic Validation | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health & diagnostics |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Beneficiation | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
8 | PLC Logic Validation | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health & diagnostics |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | In Progress | Blast Furnace | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Blast Furnace | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
8 | PLC Logic Validation | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health & diagnostics |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | In Progress | SMS-2 | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | SMS-2 | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | In Progress | Power Plant (3x130MW) | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Delayed | Power Plant (3x130MW) | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Completed | Power Plant (3x130MW) | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | Completed | Power Plant (3x130MW) | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | In Progress | Power Plant (3x130MW) | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
1 | Critical & Insurance Spares Governance | Identify, classify & validate critical and insurance spares with risk matrix |  | 2026-08-04 | In Progress | Power Plant (3x130MW) | January |  | 2026-08-04
2 | Single Point Failure Analysis | Identify all single point tripping in PLC/Drives/Field |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
3 | Pain Point Tripping Analysis | Analyze last 1-year tripping data and identify recurring failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
4 | CPU Memory & System Cleanup | Check CPU memory usage, delete temp files in EWS/OWS |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
5 | Control Philosophy Documentation | Prepare/update control philosophy for all CGL 1–6 & CCL |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
6 | PLC & Drive Backup System | Ensure latest backups (online + offline) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
7 | Modification Register | Maintain updated logic & P&ID modification records |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
8 | PLC Logic Validation with CGL | Cross-check PLC logic vs commissioning logic |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
9 | EMG Start/Stop SOP | Prepare emergency operation procedures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
10 | Shutdown Interlock Validation | Validate all interlocks during shutdown (>3 days) |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
11 | Calibration Traceability | Ensure calibration records & traceability |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
12 | PM Optimization | Review PM, calculate effectiveness & revise plans |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
13 | CAPA Implementation | RCA + CAPA for all E&I failures |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
14 | System Health Check | Monitor CPU load, network health, diagnostics |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
15 | UPS Health & Integration | Verify UPS backup & integrate signals to HMI |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
16 | Managed Switch Maintenance | Annual cycling + configuration backup |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
17 | Recurrence Tracking System | Develop failure trend & tracking mechanism |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
18 | Critical Spare Validation | Validate critical spares with failure data |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
19 | Obsolete Inventory Identification | List obsolete/unusable items |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
20 | Aging & Dead Stock Review | Analyze aging stock & action plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
21 | Inventory Norm Validation | Verify min-max levels |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
22 | Long Lead & High-Cost Items | Identify & ensure stocking strategy |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
23 | Vendor Duplication Check | Optimize vendor base |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
24 | Spare Consolidation Plan | Submit consolidated spare plan to C&I |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04
25 | Skill Gap Assessment | Identify skill gaps & training plan |  | 2026-08-04 | Open | Power Plant (3x130MW) | January |  | 2026-08-04